## DEFECT TRACKER
Development Team
DEFECT / ISSUE TRACKER
|  |  |  | User Impact | Business impact
Status | Count |  | 1-Critical | 4 | 7
1-New | 5 |  | 2-High | 8 | 9
2-Open | 12 |  | 3-Medium | 3 | 6
3-Closed | 6 |  | 4-Low | 8 | 1
TOTALS | 23 |  |  | 23 | 23
Defect ID | Detected Date | Customer ref | Status | H/M/L User impact | H/M/L Business impact | Subject | Reported by | Defect / issue description | Environment | Customer facing update | Internal Update | Assigned to
1 - Software Requirements | 2024-03-16 | 111 | 1-New | 2-High | 2-High | Incomplete Medication Tracking Requirements | Development Team | The requirements document lacks details on handling medication dosages and frequency. | QA | In Development | Details are still in the works, a consistent tracking formula will be developed soon | Development Team
2 - Software Project Plans | 2024-03-16 | 222 | 3-Closed | 4-Low | 1-Critical | Unrealistic Milestones for App Development | Development Team | The project timeline does not allocate sufficient time for the testing and validation | QA | We are reviewing our project timeline to ensure optimal testing and validation phases before release. | Adjust project timelines to accommodate different and unique testing phases, including validation checking. | Development Team
3 - Use Cases | 2024-03-16 | 333 | 3-Closed | 3-Medium | 2-High | Use Case for Profile Management | Development Team | There are no defined use cases for adding or switching between user profiles in the app. | QA | Enchanced features for managing user profiles are under development to improve your experience. | Develop and document use cases for profile management features to ensure clarity when developing. | Development Team
4 - Software Designs | 2024-03-16 | 444 | 3-Closed | 1-Critical | 1-Critical | Inadequate Error Handling in Vitals Tracking | Development Team | The software design does not specify error handling for out-of-range input for heart rate data. | Dev | We are updating our app to handle wider ranges of heart rate data inputs. | Update software design to include error handling for heart rate data inputs that fall outside expected ranges. | Development Team
5 - Software Specifications | 2024-03-17 | 555 | 2-Open | 2-High | 2-High | Unclear Connectivity Requirements | Development Team | Specifications do not clearly outline the requirements for internet connectivity during data synchronization. | QA | Our commitment is to streamline data synchronization under many connectivity conditions. | Define and document connectivity requirements to streamline the data sychronization processes. | Development Team
6 - Data Flow Diagrams | 2024-03-17 | 666 | 1-New | 2-High | 2-High | Missing Data Flow for Nutrition Output | Development Team | The diagrams do not illustrate the flow of data for the output section under Nutrition tracking. | QA | We're refining our nutritiion tracking feature to better understand and enhance your dietary patterns. | Create detailed data flow diagrams for the nutrition tracking feature to guide better and more accurate development. | Development Team
7 - Database and File Designs | 2024-03-17 | 777 | 2-Open | 1-Critical | 1-Critical | Insufficient Encryption for Sensitive Data | Development Team | Data syncing between Vita app and external health devices results in intermittent data loss, affecting user health tracking accuracy. | Dev | Improvements are being implemented to ensure seamless health data syncing across your devices. | Address and resolve the issues causing data loss during the sync process with external devices. | Development Team
8 -Online Operating Environment Specifications | 2024-03-17 | 888 | 3-Closed | 4-Low | 3-Medium | Incompatible Browser Support | Development Team | The online operation environment specs don't include support for commonly used broswers. | Dev | We're expanding our broswer compatibility to ensure everyone can use our app / add data from external browsers. | A creation of a website that houses details on the project and functionalities for the end user would be a great idea. It should also show means in which to download the app. | Development Team
9 -Batch operating environment specifications | 2024-03-17 | 999 | 3-Closed | 2-High | 2-High | Inadequate Handling of Large Data Batches | Development Team | The specifications do not address performance issues when processing large batches of health data for reports. | Dev | We are optimizing our system for handling extensive health data efficiently. | Update specifications to include performance benchmarks and potential optimization strategies for handling a large amount of data. | Development Team
10 -Interfaces | 2024-03-17 | 101 | 2-Open | 2-High | 1-Critical | Inconsistent Interface Design Across Platforms | Development Team | The app's interface design varies significantly between iOS and Android, leading to a disjointed user experience. | Dev | We are working on unifying our app's interface for a cohesive experience across all devices. | Initiate a design overhaul to unify the user interface across the different operating systems. | Development Team
11 -Connectivity Specifications | 2024-03-17 | 102 | 1-New | 3-Medium | 3-Medium | Lack of Offline Functionality Specification | Development Team | The app's network specifications do not detail the functionality available to users when offline, potentially hindering user engagement in areas with poor connectivity. | Dev | Expanding offline capabilities to keep you connected to your health goals at all times. | Document offline functionality specifications to guide the development of features accessible without internet connectivity. | Development Team
12 - Security Specifications | 2024-03-18 | 103 | 2-Open | 1-Critical | 1-Critical | Weak Authentication | Development Team | The app's security specifications fail to include multi-factor authentication for user logins. | Dev | Enhancing security with the addition of multifactor authentication for a safer application experience. | Revise security specifications to incorporate multi-factor authentication measures to enhance user accont protection. | Development Team
13 - Screen/Window/Page Specifications | 2024-03-18 | 104 | 2-Open | 4-Low | 4-Low | Screen specification errors | Development Team | The screen specifications detailed in our design documents do not match our current specifications and application. | Dev | We're updating our screen designs to enhance your user experience in Vita. | Realign screen specifications with the current design documents. | Development Team
14 -Report Specification | 2024-03-18 | 105 | 1-New | 4-Low | 3-Medium | Missing Specifications for Custom Health Reports | Development Team | The document lacks details on generating customizable reports for users, such as filtering by date range or specific health metrics. | QA | Custom report generation is being improved to give you more control of your data insights. | Document generation of customizable reports with filters for specific metrics with user accessibility in mind. | Development Team
15- Code | 2024-03-18 | 106 | 2-Open | 1-Critical | 1-Critical | Incomplete Database Storing | Development Team | The app's code contains inefficient database queries that slow down performance. | Dev | We are upgrading our database to deliver quicker and more responsive app performance. | Optimize our database queries to enhance our app speed and performance without sacrificing our quality standards. | Development Team
16 - Test Plans | 2024-03-18 | 107 | 2-Open | 3-Medium | 3-Medium | Incomplete Test Coverage for Calendar View | Development Team | The test plan does not cover all functional scenarios for the calendar view feature. | QA | We are evolving our testing to cover all aspects of our calendar view feature. | Update our test plan to include all functional scenarios for the calendar view feature, use user and stakeholder feedback to address all functionality needs. | Development Team
17 - Test Cases | 2024-03-18 | 108 | 3-Closed | 4-Low | 3-Medium | Lack of Test Cases for User Profile Switching Functionality | Development Team | The application's test documentation does not include specific test cases to verify the functionality that allows users to switch between different profiles. | QA | We plan to incorporate all sub-profiles under one main profile. No need to authenticate everytime | Implementing a main user feature to manage multiple profiles, simplifying authentication and enhancing usability. | Development Team
18 -Test Environment Specification | 2024-03-18 | 109 | 2-Open | 4-Low | 2-High | Incomplete Specification for Cross-Device Testing | Development Team | The specifications do not include requirements for testing the app across different devices and operating systems, which is critical for ensuring compatibility. | QA | Our app will soon be tested across all devices to ensure a seamless experience no matter the device. | Update our specifications and plans to ensure testing across all supported devices and operating systems is done efficiently, and ensure quality is met across each platform. | Development Team
19 -Test Data Sources and Preparation | 2024-03-18 | 110 | 2-Open | 4-Low | 2-High | Inadequate test data preparation | Development Team | Test data sources lack diversity, and preparation steps aren't clearly detailed in our planning phases, which affect test quality and coverage. |  | We are enhancing our test data to imrpove quality and reliability in Vita. | Update and improve test data sources and detail all preparation steps required before commencing our testing. | Development Team
20 -Test Tools Installations and Operation | 2024-03-18 | 201 | 2-Open | 4-Low | 2-High | Unspecified Test Tools for Performance Testing | Development Team | The documentation does not specify which tools should be used for performance testing, leading to inconsistency in test results. | QA | We are standardizing our performance testing approaches to maintain the highest quality standards. | Identify and document standardized performance testing tools and methodologies for consistent implementation to ensure accurate results when testing. | Development Team
21 - Installation Guides | 2024-03-18 | 202 | 1-New | 2-High | 1-Critical | Incomplete Installation Steps | Development Team | There are no installation steps created for IOS and Android devices | QA | We're developing easy-to-follow installation guides to get you started on any device. | Draft detailed and comprehensive installation instructions for both iOS and Android platforms. | Development Team
22 - Operation/Administration Guides | 2024-03-19 | 203 | 2-Open | 2-High | 3-Medium | Lack of Troubleshooting Section | Development Team | The administration guide does not include a troubleshooting section for common issues encountered by users. | QA | Soon you'll have access to a detailed troubleshooting section for common issues encountered by users. | We need to incorporate a troubleshooting section such that the end user may be able to resolve common problems without resulting in abandoning or leaving the app. This will be appropriate in the settings screen. | Development Team
23 - User Guides | 2024-03-19 | 204 | 2-Open | 2-High | 2-High | Vague Instructions on Medication Logging | Development Team | The user guide provides vague instructions on how to log medication, leading to potential misuse of the feature. | QA | We are clarifying the medication logging process in our user guide to enhance understanding and accuracy. | The user guide needs to be comprehensive and easy to understand, it must set out clear and straightforward instructions. The targeted audience are the elderly and children/new mothers. It is imperative everything is clear and understandable. | Development Team
24 - Help Screens | 2024-03-19 | 205 | 2-Open | 3-Medium | 3-Medium | Non-Existing Help Screen | Development Team | The help screens lack detailed explanations on how to input and track data | Dev | Detailed help content is being added to guide you through the data input and tracking features within the app. | A help screen should be implemented in the settings page as well, maybe a modal pop-up. | Development Team
25 -Training Manuals | 2024-03-19 | 206 | 1-New | 4-Low | 4-Low | Non-Existing Training material | Development Team | There needs to be an incorporation of a training manual | QA | We're developing a comprehensive training manual to ensure you get the most out of Vita. | We need to create a comprehensive step-by-step instruction manual for the end user. This is important in the sense that it will allow for ease of use from the end users perspective. | Development Team

## RESOURCES
Issue Log
Test Case Template
Project Status Report
Lessons Learned Template
Post Project Review Template
Change Request Template
Top 20 Common Project Risks

## Dropdowns
Status
1-New
2-Open
3-Closed
[Blank]
Severity
1-Critical
2-High
3-Medium
4-Low
[Blank]